**Nigeria Group Work**

What do we do?

**Note:** Actions will be targeted for commemorative days (Workers day, democracy day, Industrialisation day, Independence day) actions will also be targeted at key moments (Africa Ministers of Finance Meetings, Regional and Continental Fora, National Economic Summit Group Meetings et al)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Activity** | **Strategy** | **Responsibility (Task Bearer)** | **Target Groups** | **Time Frame** | **Expected Outcome** | **Resource Needed** |
| Advocacy at the Leadership and organs levels of the trade unions and NGOs to have commitment | Briefing of Leadership and Organs | NLC/TUC/TJ&GP Secretariats | National, State and Branch union leaders | February - March | Commitment from the leadership of the labour centres |  |
| Define strategies and action plans | Holding material development meeting | NLC/TUC | Research units and leadership | March | Strategy and work plan | TJ&GP |
| Build alliances and collaboration with the media and other stakeholders | Press Statements and Releases, advocacy meetings, sign into existing activities | NLC/TUC | Print and electronic media, stakeholders (NGOs, Professional bodies, FIRS et al) | Ongoing | * Consolidate the emergence of a broad based platform for tax justice; * Organise collaborative advocacy work and manifestations |  |
| Knowledge building and awareness through the trade unions organisational and educational programmes | Collective meetings, Using the trade union educational structures and Media briefings  Key into capacity building initiatives by the TJ&GP members | NLC/TUC/TJ&GP | Rank and file members and the general public | April - December | * Increased awareness of rank and file workers on the tax justice campaign; * Enhanced enlightenment of economy operators on tax justice and related issues School * Baseline information and data available for further engagement |  |
| Review of Existing and relevant tax laws | Looking at Existing legislation and making proposals | NLC/TUC/TJ&GP | National Assembly, Tax Administrators and Tax payers | June-September | * Policy brief developed * Tax charter of demand formulated |  |
| Consultation, Engagement with relevant stakeholders | Advocacy visits to National Assembly, legislative briefings, Tax Administrators, Ministry of Finance and relevant stakeholders | NLC/TUC | Relevant Stakeholders and general public, | June-July | * Put the 'Tax for Public Service delivery' in the national development discuss discourse |  |

**What is on-going?**

- A structure created for the Tax Justice and Governance platform (Relationship building and solidarity)

- Key researches done and more on the way on different issues of tax by different organisations (Access to baseline information)

- FIRS developing the 'Presumptive Tax Regime' targeted at the informal sector (analysis and consultation on the PTR)

- On-going initiative for alternative financing and tax justice movement taking place at different levels