**WORKPLAN EATUC**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| What | How | Who | When | Outcomes |
| Commitment from EATUC Summit | Concept note presented to the Summit | EATUC Affiliates and Co-operating Partners | 3RD February 2014 | EATUC Resolution on Tax Justice |
| Develop an EATUC Tax Justice Advocacy Strategy Focusing on Social Security and the Extractive Industry in EAC | Using the Tax Justice Advocacy Toolkit | Tax Justice, Action Aid, ITUC-Africa, FES-Tanzania | End of March 2014 | A clear EATUC Tax Justice Advocacy Strategy |
| Develop EATUC Key Messages in form of IEC material on Tax Justice with regards to Social Security and Extractive Industry | Committee of Experts | LO-Norway and FES | 3rd Quarter 2014 | IEC Material |
| Launching EATUC Tax Justice Regional Campaign | Media Press release, Session with EALA Members | Tax Justice Network, ITUC-Africa, FES-Tanzania, EACSOF, National Centers | 3rd Quarter 2014 | Press release, Comments from EALA Members |
| Roll out National Campaigns with Country Specific Messages | Using the Tax Justice National platforms | Affiliates | 3rd quarter | National Action Plans |